THE THIRD PLACE FINDER Project Roadmap · Team Division · Integration Checkpoints Emerald Forge Hackathon · Seattle, WA · Mar 17 – Mar 26, 2025

01 PROJECT ROADMAP The project runs from March 17 to March 26 — 10 days split into four focused phases. Each phase has a clear set of deliverables and a designated primary owner, with all four members converging for integration and final QA. PHASE; DELIVERABLES; OWNER; DATES; STATUS. Phase 1 Foundation; - Repo setup, branching strategy, CI skeleton - Seed JSON schema design (60+ venues, tagging spec) - FastAPI app scaffolding + health endpoint - React + Vite + Tailwind project init on Vercel; All 4 members; Week 1 Mar 17–21; Planned. Phase 2 Core Agents; - LangGraph state machine skeleton + AppState dataclass - Profiler Agent — onboarding prompt + preference vector - Scout Agent — Overpass API + seed JSON query logic - Ranker Agent — LLM scoring + explanation generation; Members 1 & 2; Week 2 Mar 22–25; Planned. Phase 3 Memory & Map; - Memory Agent — ChromaDB embedding store + retrieval - FastAPI endpoints wiring all four agents end-to-end - Leaflet.js map — pins, popups, vibe-tagged cards - React chat UI — onboarding flow + results panel; Members 3 & 4; Week 3 Mar 22–25; Planned. Phase 4 Integration; - Frontend ↔ Backend API integration + CORS config - Cross-session memory tested across 3+ user flows - Render.com backend deploy + Vercel frontend deploy - End-to-end QA across Chrome, Safari, mobile viewports; All 4 members; Week 4 Mar 25–26; Planned. Phases 2 and 3 run in parallel during Week 2: while Members 1 & 2 build the AI agent pipeline, Members 3 & 4 build the backend API and frontend UI. All four streams converge in Week 4 for integration, deployment, and submission. 02 TEAM DIVISION — ROLES & RESPONSIBILITIES Each member owns a distinct technical layer of the stack. Ownership means: you design it, build it, test it, and document it. Cross-member dependencies are resolved at the daily 15-minute standups and the three integration checkpoints below. Member 1 — Team Lead & AI Agents - LangGraph state machine & AppState schema - Profiler Agent — onboarding dialogue + preference embedding - Ranker Agent — LLM scoring logic & explanation prompts - Agent integration testing & prompt tuning - Final review & submission coordination Stack: LangGraph · Groq API · LLM prompting · Python; Member 2 — Data & Scout Agent - Curated Seattle seed JSON — 60+ venues, tagging schema - Scout Agent — Overpass API queries + seed JSON lookup - Venue attribute schema (noise, outlets, Wi-Fi, hours) - Data validation & neighbourhood coverage QA - Support Ranker with candidate shortlisting logic Stack: Python · Overpass API · JSON · data curation. Member 3 — Backend & Memory Agent - FastAPI app — REST endpoints, Pydantic v2 schemas - Memory Agent — ChromaDB vector store + retrieval logic - sentence-transformers embedding pipeline - CORS config, Render.com deploy & environment setup - API contract docs for frontend handoff Stack: FastAPI · ChromaDB · sentence-transformers · Render; Member 4 — Frontend & Map UI - React 18 + Vite + Tailwind project setup - Conversational onboarding chat UI component - Leaflet.js map — pins, popups, vibe-tagged result cards - Results panel — noise/outlet/Wi-Fi badges + distance - Responsive design QA (Chrome, Safari, mobile) Stack: React 18 · Leaflet.js · Tailwind CSS · Vercel. 03 INTEGRATION CHECKPOINTS Three hard checkpoints gate progress before the final submission. If a checkpoint is missed, the team pauses new feature work and fixes the blocker together. CHECKPOINT DATE; DONE-WHEN CRITERIA. Mar 21 (end of Wk 1); Repo live, seed JSON schema agreed, CI passing, FastAPI health endpoint green, React app deploys to Vercel preview URL. Mar 23 (mid Wk 2); Profiler + Scout + Ranker agents callable via FastAPI; Leaflet map renders with hardcoded pins; Memory Agent stores first embedding. Mar 25 (start Wk 4); Full agent pipeline returns top-3 results end-to-end; frontend chat UI talks to backend; cross-session memory confirmed across 3 flows. Mar 26 (submission); Public URL live on Render + Vercel; QA across 3 browsers; design doc updated; README with setup instructions merged. 04 COLLABORATION NORMS Git Workflow Main branch is protected — no direct pushes. All work goes through feature branches (feature/agent-profiler, feature/scout-api, etc.) and is merged via pull request with at least one reviewer approval. Branch naming: feature/<member>-<component>. Daily Standups 15-minute async standup in Slack each morning: (1) what I shipped yesterday, (2) what I am doing today, (3) any blockers. Blockers flagged by 10 AM get a same-day resolution discussion. API Contract First Member 3 publishes the FastAPI endpoint schema (request/response Pydantic models) by end of Phase 1 so Members 1, 2, and 4 can develop against a stable contract without waiting for the backend to be fully built. Mock responses ship in Week 1. Definition of Done A task is done when: (a) it passes local tests, (b) it is merged to main, (c) it is demo-able to the team, and (d) relevant README section is updated. Deployment to Render/Vercel counts as done only when the public URL returns the expected response. Third Place Finder · Emerald Forge Hackathon 2025 · Seattle, WA · Roadmap v1