THE THIRD PLACE FINDER Detailed Task Breakdown · All 4 Members · 10-Day Sprint Emerald Forge Hackathon · Seattle, WA · Mar 17 – Mar 26, 2025

Each task below is sized to be completable in a single focused session (30 min – 1.5 hrs). Tasks are sequenced so that dependencies are clear — if a task has a hard prerequisite, that prerequisite appears first. The checkbox column (□) is designed to be printed or filled in a shared Notion/Linear board. M1 MEMBER 1 — TEAM LEAD & AI AGENTS Member 1 Team Lead & AI Agents LangGraph orchestration · Profiler Agent · Ranker Agent · CI & architecture Stack: LangGraph 0.2 · Groq API (Llama 3.3 70B) · Python · pytest · GitHub Actions. #; TASK; EST.. Phase 1 — Foundation Mar 17–21 ¦ Est. total: ~5 hrs. □; 01; Create GitHub repo — init monorepo, set branch protection on main, invite all members. □; 02; Define AppState dataclass — draft the shared LangGraph state schema (fields: user_prefs, candidates, ranked, memory_context). □; 03; Scaffold LangGraph skeleton — blank graph with 4 named nodes and pass-through edges, confirm it runs end-to-end. □; 04; Write agent interface spec — document the input/output contract each agent must honour (shared with team). □; 05; Set up CI — GitHub Actions workflow: lint + pytest on every PR to main. Phase 2 — Profiler Agent Mar 22–23 ¦ Est. total: ~6 hrs. □; 06; Write onboarding prompt — 5-question dialogue covering noise, group size, time of day, outlet need, caffeine. □; 07; Parse user answers — extract structured preference dict from LLM response using regex + fallback defaults. □; 08; Build preference embedding — convert preference dict to a text string, embed via sentence-transformers. □; 09; Unit test Profiler — 3 test cases: solo night-owl, group morning, silent afternoon. □; 10; Wire Profiler into LangGraph — confirm AppState.user_prefs is populated after node runs. □; 11; Write Profiler README section — explain the prompt design and output format. Phase 2 — Ranker Agent Mar 23–24 ¦ Est. total: ~5 hrs. □; 12; Design scoring prompt — instruct LLM to score each candidate 0–10 across 4 axes: noise fit, outlet fit, distance, vibe. □; 13; Build score parser — extract JSON scores from LLM response, handle malformed output gracefully. □; 14; Generate explanation strings — one sentence per top-3 spot explaining why it fits this user. □; 15; Unit test Ranker — verify correct top-3 ordering for 3 mock candidate sets. □; 16; Wire Ranker into LangGraph — confirm AppState.ranked is populated correctly. □; 17; Prompt-tune for edge cases — test with 0 candidates, 1 candidate, all same score. Phase 4 — Integration & Lead Mar 25–26 ¦ Est. total: ~4 hrs. □; 18; End-to-end agent pipeline smoke test — run full flow from onboarding to ranked results, log each step. □; 19; Fix inter-agent bugs — resolve any AppState mismatches found during integration. □; 20; Code review all PRs — review and merge open PRs from Members 2, 3, 4 before submission. □; 21; Update design doc — add actual model names, prompt versions, and final agent architecture to design doc v4. □; 22; Record 2-min demo video — screen-capture the full user flow for submission.. Total estimate: ~5 hrs, ~6 hrs, ~5 hrs, ~4 hrs across all phases M2 MEMBER 2 — DATA & SCOUT AGENT Member 2 Data Curation & Scout Agent Seed JSON dataset · Overpass API integration · Scout Agent · Data quality Stack: Python · Overpass API · JSON schema design · pytest. #; TASK; EST.. Phase 1 — Seed Data Schema Mar 17–20 ¦ Est. total: ~5 hrs. □; 01; Design venue JSON schema — define all fields: name, address, lat/lng, neighbourhood, noise_level (1–5), outlets (none/few/many), wifi_quality (poor/ok/fast), hours, group_max, tags[]. □; 02; Share schema with team — post schema to Slack and get sign-off from Members 1 and 4 before populating data. □; 03; Research 60+ Seattle venues — identify real cafes, libraries, co-working spaces across Capitol Hill, SLU, Fremont, U-District, Belltown, Pioneer Square. □; 04; Populate seed JSON — write all 60+ entries conforming to the schema, validate JSON syntax. Phase 2 — Scout Agent Mar 21–24 ¦ Est. total: ~7 hrs. □; 05; Load seed JSON — function to parse and index seed_venues.json into memory at startup. □; 06; Build seed lookup — filter venues by neighbourhood, noise level, group size, and outlet tags from user_prefs. □; 07; Integrate Overpass API — query for amenity=cafe + amenity=library within 1 km of user location. □; 08; Normalise Overpass results — map Overpass response fields to the same schema as the seed JSON. □; 09; Merge + deduplicate candidates — combine seed and Overpass results, remove duplicates by lat/lng proximity. □; 10; Unit test Scout — 3 test cases: Capitol Hill solo, U-District group, Belltown no outlets. □; 11; Wire Scout into LangGraph — confirm AppState.candidates is populated from seed + Overpass. Phase 3 — Data Quality Mar 24–25 ¦ Est. total: ~3 hrs. □; 12; Validate all 60+ venue entries — check every field is present, lat/lng is valid, hours string is parseable. □; 13; Add busyness-by-hour heuristics — for each venue add a busy_hours array (e.g. [12,13,18,19]) based on real-world observation. □; 14; Neighbourhood coverage check — ensure minimum 8 venues per neighbourhood, fill gaps. □; 15; Write data README — document schema, how to add new venues, and Overpass query parameters. Phase 4 — Integration Mar 25–26 ¦ Est. total: ~2 hrs. □; 16; Integration test Scout with real Profiler output — run full Profiler → Scout flow, verify candidate count > 0. □; 17; Fix field mismatches — resolve any schema differences between seed JSON and what Ranker expects. □; 18; Document 5 sample venues in README — include as example output for judges reviewing the submission.. Total estimate: ~5 hrs, ~7 hrs, ~3 hrs, ~2 hrs across all phases M3 MEMBER 3 — BACKEND & MEMORY AGENT Member 3 Backend & Memory Agent FastAPI REST API · ChromaDB vector memory · Render.com deploy · API contract Stack: FastAPI 0.111 · ChromaDB 0.5 · sentence-transformers · Render.com · Pydantic v2. #; TASK; EST.. Phase 1 — Backend Scaffold Mar 17–21 ¦ Est. total: ~6 hrs. □; 01; Init FastAPI project — pyproject.toml, folder structure (app/, agents/, memory/, tests/), requirements.txt. □; 02; Build health endpoint — GET /health returns {"status":"ok","version":"1.0"}, deploy to Render, share URL. □; 03; Define Pydantic schemas — UserPrefs, Candidate, RankedResult, SessionRequest, SessionResponse models. □; 04; Publish API contract — post OpenAPI spec (auto-generated at /docs) to Slack for Member 4 to build against. □; 05; Set up Render.com — create web service, link GitHub repo, set environment variables (GROQ_API_KEY etc.). □; 06; Add CORS middleware — allow requests from Vercel preview URL and localhost:5173. □; 07; Write backend README — setup instructions, how to run locally, env var list. Phase 2 — Memory Agent Mar 22–24 ¦ Est. total: ~6 hrs. □; 08; Init ChromaDB collection — create persistent local collection "user_sessions" with cosine similarity. □; 09; Build embed function — use sentence-transformers all-MiniLM-L6-v2 to embed preference dicts as strings. □; 10; Store session — save (embedding, user_prefs, ranked_results, timestamp) after each completed session. □; 11; Retrieve similar sessions — query top-3 nearest sessions by embedding distance, return as memory_context. □; 12; Unit test Memory Agent — verify store + retrieve round-trip for 3 mock sessions. □; 13; Wire Memory into LangGraph — inject retrieved memory_context into AppState before Profiler runs. Phase 3 — Agent API Endpoints Mar 24–25 ¦ Est. total: ~4 hrs. □; 14; POST /session — accept UserPrefs, run full LangGraph pipeline (Profiler→Scout→Ranker→Memory), return RankedResult[]. □; 15; GET /session/{id} — return stored session details for a given session ID. □; 16; Error handling middleware — catch agent exceptions, return structured 422/500 JSON errors. □; 17; Load test — run 10 concurrent /session requests, confirm response time < 8 s each. □; 18; Deploy to Render — push final backend, confirm public URL is stable. Phase 4 — Integration Mar 25–26 ¦ Est. total: ~3 hrs. □; 19; Integration test with Member 4 — confirm frontend /session call returns correct JSON structure. □; 20; Fix CORS issues — resolve any preflight errors found during frontend integration. □; 21; Confirm memory persists across sessions — run 3 sequential sessions, verify memory_context improves. □; 22; Final Render deploy — ensure latest main branch is live, check logs for errors.. Total estimate: ~6 hrs, ~6 hrs, ~4 hrs, ~3 hrs across all phases M4 MEMBER 4 — FRONTEND & MAP UI Member 4 Frontend & Map UI React chat UI · Leaflet.js interactive map · Result cards · Responsive QA Stack: React 18 · Vite · Tailwind CSS · Leaflet.js · react-leaflet · Vercel. #; TASK; EST.. Phase 1 — Frontend Scaffold Mar 17–21 ¦ Est. total: ~5 hrs. □; 01; Init React 18 + Vite + Tailwind — npx create-vite, add Tailwind v3, confirm blank app deploys to Vercel. □; 02; Set up Vercel project — link GitHub repo, configure preview URL per branch, share URL with team. □; 03; Create component folder structure — /components/Chat, /components/Map, /components/ResultCard, /hooks, /api. □; 04; Build API client module — api/session.js with postSession(prefs) function using fetch + base URL from env. □; 05; Add .env.local — VITE_API_URL pointing to Member 3's Render URL, document in README. □; 06; Build loading skeleton — spinner component shown while awaiting API response. □; 07; Write frontend README — local setup, env vars, how to run alongside backend. Phase 2 — Chat UI Mar 22–23 ¦ Est. total: ~5 hrs. □; 08; Build ChatWindow component — scrollable message thread, renders user and AI bubbles differently. □; 09; Build MessageBubble component — user bubble (right, purple), AI bubble (left, light lavender). □; 10; Onboarding question flow — step through 5 questions (noise, group size, time, outlets, caffeine) collecting answers. □; 11; Preference state management — useReducer hook accumulating answers into a UserPrefs object. □; 12; Submit button + API call — on final answer, POST to /session, disable button and show spinner. Phase 3 — Map & Result Cards Mar 23–25 ¦ Est. total: ~6 hrs. □; 13; Integrate Leaflet.js — npm install leaflet react-leaflet, render a MapContainer centred on Seattle. □; 14; Add venue pins — drop a Marker for each of the top-3 results using lat/lng from API response. □; 15; Build Popup component — clicking a pin shows name, noise badge, outlet badge, walking distance. □; 16; Build ResultCard component — ranked list below map showing rank number, name, vibe tags, AI explanation sentence. □; 17; Noise / outlet / Wi-Fi badges — colour-coded pill components (green/amber/red) based on venue attributes. □; 18; Distance calculation — compute walking distance from a fixed Seattle centroid using Haversine formula. Phase 4 — Polish & QA Mar 25–26 ¦ Est. total: ~4 hrs. □; 19; Mobile responsive layout — test and fix layout on 375 px (iPhone SE) and 390 px (iPhone 14) viewports. □; 20; Cross-browser QA — run full user flow in Chrome, Safari, and Firefox, fix any rendering differences. □; 21; Error state UI — show friendly message if API call fails, with a "Try again" button. □; 22; Empty state UI — handle case where API returns 0 results gracefully. □; 23; Final Vercel deploy — merge main, confirm production URL is live and stable. □; 24; Screenshots for submission — capture onboarding, map with pins, and result cards for the README.. Total estimate: ~5 hrs, ~5 hrs, ~6 hrs, ~4 hrs across all phases Third Place Finder · Task Breakdown v1 · Emerald Forge Hackathon 2025 · Seattle, WA